## Bug Report V1
Defect ID | status | raised by | test case id | steps to reproduce | test environment | expected result | actual result | priority | severity
1 | opened | basel osama | new customer_0026 | 1- press space before writing first character in state field | v1 | error msg"space are not allowed | error msg"number are not allowed" | medium | medium
2 | opened | basel osama | New customer_0033 | 1- press space before writing first character in pin field | v1 | error msg"space are not allowed | error msg"number are not allowed" | medium | medium
3 | opened | basel osama | new customer_0025 | 1- press space before typing first number | v1 | error msg"space are not allowed | error msg " characters are not allowed" | medium | medium
4 | opened | basel osama | New customer_0040 | 1- press space before typing first number | v1 | error msg " space are not allowed" | error msg " characters are not allowed" | medium | medium
5 | opened | basel osama | new customer_0042 | 1-enter phone number contianing from 1 number | v1 | error msg " invalid phone number" | no error msg is appear | medium | medium
6 | opened | basel osama | New customer_0046 | 1-press space before first character 2- press TAB to move to next field | v1 | error msg " space are not allowed" | error msg "invalid email id" | medium | medium
7 | opened | basel osama | Ec_form_0005 | 1- enter space before enter first number in customer id field 2- press TAB to go to next step | v1 | error msg " space are not allowed" | no error msg is appear | medium | medium
8 | opened | basel osama | delete customer_005 | 1- press space before first character 2-press TAB to move to next field | v1 | error msg"space are not allowed " | error msg "character are not allowed" | medium | medium
9 | opened | basel osama | add new account _002 | 1- don't enter value in customer id field 2-press TAB to move to another field | v1 | error msg" customer id field must not be blanked" | no error msg is appear | medium | medium
10 | opened | basel osama | add new account _003 | 1- writing special character in customer id field 2- press TAB to move to next field | v1 | error msg "special character not allowed" | no error msg is appear | medium | medium
11 | opened | basel osama | add new account _004 | 1- enter character in customer id field 2-press TAB to move to next field | v1 | error msg " special char5are not allowed" | no error msg is appear | medium | medium
12 | opened | basel osama | add new account_005 | 1- press space before first character 2-press TAB to move to next field | v1 | error msg " space not allowed " | no error msg is appear | medium | medium
13 | opened | basel osama | add new account _007 | 1- don't enter value in initial deposit field 2- press TAB to move to next field | v1 | error msg "initial deposit field must not be blanked" | no msg is appear | medium | medium
14 | opened | basel osama | add new account_008 | 1- enter character in initial deposit field 2- press TAB to go to next field | v1 | error msg" character ate not allowed" | no error msg is appear | medium | medium
15 | opened | basel osama | add new account _009 | 1- enter special character in initial deposit 2-press TAB to move to next field | v1 | error msg"character are not allowed" | no error msg is appear | medium | medium
16 | opened | basel osama | add new account_010 | 1- enter space before first number in initial deposit field 2- press TAB to move to next field | v1 | error msg" space are not allowed " | no error msg is appear | medium | medium
17 | opened | basel osama | add new account _011 | 1- enter negative amount in initial deposit field 2- press TAB to move to next field | v1 | error msg" in valid amount " | no error msg is appear | medium | medium
18 | opened | basel osama | edit account _005 | 1- enter space before writing first number in account number field 2- press TAB to move to next field | v1 | error msg"space are not allowed " | error msg"character are not allowed" | medium | medium
19 | opened | basel osama | edit account _006 | 1- enter account number with space between number 2- press TAB to move to next Field | v1 | error msg"space are not allowed " | error msg "character are not allowed" | medium | medium
20 | opened | basel osama | delete account_005 | 1- enter space before writing first number in account number field 2- press TAB to move to next field | v1 | error msg"space are not allowed " | error msg"character are not allowed" | medium | medium
21 | opened | basel osama | delete account_006 | 1- enter account number with space between number 2- press TAB to move to next Field | v1 | error msg"space are not allowed " | error msg "character are not allowed" | medium | medium
22 | opened | basel osama | mini statement_005 | 1- enter space before first number in account number 2- press TAB to move to next field | v1 | error msg" space are not allowed" | error msg " character are not allowed" | medium | medium
23 | opened | basel osama | customized statement_005 | 1- enter space before first number in account number 2- press TAB to move to next field | v1 | error msg" space are not allowed" | error msg"character are not allowed" | medium | medium
24 | opened | basel osama | customized statement_007 | 1- don't enter any value in start date 2- press TAB to move to next field | v1 | error msg" start date must not be blanked" | no error msg is display | medium | medium
25 | opened | basel osama | customized statement_008 | 1- don't select any value in end date field 2- press TAB to move to next field | v1 | error msg" end date must not be blanked" | no error msg is display | medium | medium
26 | opened | basel osama | customized statement_010 | 1- don't enter value in lower limit field 2- press TAB to move to next dield | v1 | error msg "lower limit field must not be blanked" | no error msg is displayed | medium | medium
27 | opened | basel osama | customized statement_011 | 1- enter character in lower limit field 2- press TAB to move to next field | v1 | error msg"character are not allowed" | no error msg is displayed | medium | medium
28 | opened | basel osama | customized statement_012 | 1- enter special character in lower limit field 2- press TAB to move to next field | v1 | error msg"special character are not allowed" | no error msg is displayed | medium | medium
29 | opened | basel osama | customized statement_013 | 1- press space before first number 2- press TAB to move to next field | v1 | error msg "space are not allowed" | no error msg is displayed | medium | medium
30 | opened | basel osama | customized statement_0015 | 1- don't enter value in number of transactions field 2- press TAB to move to next field | v1 | error msg" number of transactions field must not be blanked" | no error msg display | medium | medium
31 | opened | basel osama | customized statement_0016 | 1- enter character in number of transactions field 2- press TAB to move to next field | v1 | error msg"character are not allowed" | no error msg is displayed | medium | medium
32 | opened | basel osama | customized statement_0017 | 1- enter special character in number of transactions field 2- press TAB to move to next field | v1 | error msg "special character are not allowed" | no error msg is displayed | medium | medium
33 | opened | basel osama | customized statement_0018 | 1- press space before first number in number of transactions field 2- press Tab to move to next field | v1 | error msg"space are not allowed" | no error msg is displayed | medium | medium